## Sheet1
Date | Hours | Description
2016-02-04 | 3.5 | Added Creature/Player HP/Attack/Defence, CombatStyle, GlobalConstants, Tile, DrawGrid()/DrawLine(), LoadTiles(), SelectTile(), UpdateTiles() | Total Hours Spent Programming: | 22
2016-02-05 | 4 | Reprogrammed game to use GraphicManager/InputManager/GameState/UIScreens | Total Days Worked: | 5
2016-02-06 | 7 | Revised Level loading - now contains spawn data. Added OriginPosition to GameObject. Player Creation. Player movement - WASD key bindings. Levels can now be irregular. Fixed level data orientation. Tile movement now free. Player/Tile colision checks. Added input delay for better diagonal handling, holding down a key skips the delay.
2016-02-07 | 6 | Player position now updates while grid is moving to prevent the sprite from jumping around. Removed IsMoving boolean. Levels can now have gaps within their bounds. Renamed GamePlay classes/variables to OverWorld. Renamed project to "Broken Shadows". Migrated Level loading to read from an Xml file and divided LoadLevel() into separate methods. Successfully changed xml importing to convert to xnb (4 hours for this? really?).
2016-02-08 | 1.5 | Finished level 1 xml file. Combined level layout/metadata. Changed jagged arrays to rectangular. Diagional movement now checks adjacent tiles - can no longer move diagonally through walls. Added IsRigid property to tiles + moveable tile type. Updated player texture. Grid panning now uses a grid step constant, which is 1/2 the player movement speed.
Next Up: Moveable tile movement.